## Flowchart
MWS Process Chart for Organizing Internal Events
Client Proceed with MWS
Client Training Requirement
MWS Learners Kit Order
MWS Trainer Confirmation
Logistics Confirmation
Training Day
Follow up
Venue Date / Time Equipment Req Seatings F&B
Title Professional Fee Pax Demographics Special Needs
Total required Shipment Cost Total Amount
Registration Pax List MWS Learners Kit Nametags
Room Setup Room Signs Buntings Flyers Sitting Arrangements
Final Check Projector Presentation Sound Systems Flipcharts
Welcome Note to Pax
Thank You Note MWS Trainer
Thank You Note Participants
Thank You Note Organizer

## Timeline
Timeline for Organizing an MWS Workshop
# | Tasks | Days | Start | Finish | Assignments | Notes
1 | Needs Analysis with Client |  |  |  | Account Mgr
2 | Develop a needs analysis
3 | Identify Likely Attendees | 1 |  |  | Account Mgr
4 | Demographics of attendees | 1 |  |  |  | Level of education, experience? Previous trainings?
5 | Check number of attendees allowed | 1
6 | Confirm clients requirements |  |  |  |  | venue, timing, dates, etc
7 | Coordinate with MWS HQ
8 | Identify Potential MWS Trainer [Pro] | 7 |  |  | Sales Mgr | Web resources
9 | Agree on cost / time / venue | 1
10 | Get a copy of the title outline | 1
11 | Obtain MWS Trainer's profile | 1
12 | Get a preliminary cost estimate | 1 |  |  |  | check travel & expenses
14 | Confirm MWS Workshop Bookings | 1 |  |  |  | event booking confirmation form
15 | Complete Contract Requirements
16 | Client Acceptance
17 | Endorse training agreement | 1 |  |  |  | Highlight the cancellation & postponement clauses.
18 | Logistical Planning | 6
19 | Arrange for training site | 1 |  |  |  | Local hotel or internal training room?
20 | Confirm seating arrangements |  |  |  |  | Recommended theather seating
21 | Equipment Required |  |  |  |  | projector, speakers, etc.
22 | Plan and order for material shipment | 1 |  |  |  | MWS Learners Kit
23 | Send reminder to participants | 1 |  |  |  | MWS Welcome Note
24 | Plan F&B for attendees [if required] | 1
25 | Make hotel reservation for the trainer [if required] | 1 |  |  |  | Local hotel or internal training room?
26 | MWS Workshop Delivery | 1
27 | Collect participant evaluations | 1 |  |  |  | MWS Voice Count
28 | Distribute certificates | 1 |  |  |  | Check spelling, titles, etc.
29 | Follow-up | 3
30 | Thank you Note to pax |  |  |  |  | After: 3days, 14days, 30days
31 | Thank you Note to organizer | 1 |  |  |  | include pax voice count
32 | Send voice count / pax list to MWS |  |  |  |  | to ensure that your pax are in the pool of the lucky draw
33 | Plan For Next Steps | 1

## Checklist
Checklist for MWS Workshops Event
Pre-Event
Confirm | Client Acceptance | Packing List | Laptop | Venue | Seating Arrangements
| Number of Pax |  | Projector |  | F&B Arrangement
| Pax Demographics |  | Video Camera |  | Projector
| MWS Title |  | Cameras, etc |  | Projector Screen
| MWS Trainer Pro |  | Audio Speakers |  | Mic / Lapel Mic
| Event Location / Location Map |  | Registration Table items |  | Sound systems
| Event Dates / Time |  | Signages |  | Flipcharts [2x]
| Send Welcome Note |  | Gifts / Chocolates
Event Day
Signage | Register Here! | Registration | Participants List | Crew | Dresscode: Black / Orange
| Room signs | Table | MWS Learners Kit |  | Important Numbers
| MWS Buntings |  | Permenant Marker Pen |  | Nametags
| Masking Tapes |  | MWS Nametag sticker
| Blue Tags |  | Pens / Staplers
Business Namecards
After Event
To do | Consolidate Voice Count | Thank You | Pax | Followup | Next title
| Submit Pax List to MWS | Note | Organizer
Trainer

## Pax List
MWS Workshop Participants List
| MWS Workshop Title: |  |  | Venue
| MWS Trainer: |  |  | Date:
| MWS Client: |  |  | Time:
# | Name | Designation | Dept | Email | Mobile | Signature
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20

## Bookings
MWS Event Booking Confirmation
Event Information
| MWS Workshop Title: |  | Venue:
Date:
Time:
Client Information
| Company Name: |  | Tel:
| Contact Person: |  | Mobile:
| Designation: |  | Email:
Participants Information
| Number of Pax |  | Special
| Level in Organization | Non-Exec Exec Mgmt C-Level | Notes
MWS Order
1 | Name of Trainer |  | No of runs | 1
| Tel: |  | $ per run | 1500
| Email: |  | Total |  | 1500
2 | Learners Kit Order |  | No of Kit | 30
|  |  | Unit Price | 30
|  |  | Shipment | 0
|  |  | Total Price |  | 900
| Total |  |  |  | 2400
MWS Premium Reseller Information
| Company Name: |  | I hereby submit the following order:
Name of contact:
Tel:
Email:
Signature
* Please ensure you get confirmation in writing after your submission of order
Order Confirmation
We hereby accept the order
Name of Coordinator:
Tel:
Email:
Signature